## Cover
This tab is for NHS Digital use only and relates to the TOM template
NHS Digital NRLS - Target Operating Model (TOM) Self-Evaluation Checklist
Description | Self-certification tool and development and assessment framework detailing the risks, approvals, requirements and information to ensure the locally developed system meets the technical, IG, Clinical safety and functionality required for the business context |  | KEY FOR COMPLETION The colour key used throughout this document is:
Document Ref | Target Operating Model - NRLS - Self-Evaluation Checklist |  | NHS Digital to complete
Date | 2018-05-03 |  | Supplier to complete
Version | 0.4 |  | End User organisation to complete
Status | Draft |  | Supplier/End User collaborate to complete
Document History
Version | Version Description | Date of Production | Author | Change ID
0.1 | draft for review - based on TEMPLATE Target Operating Model - Spine Mini Service v1.2 | 2018-03-14 | NS | N/A
0.2 | changes after review - include The ‘Read’, ‘Update’ and ‘Delete’ and change search error code | 2018-03-28 | NS | N/A
0.3 | changes after review for service tab and changes to tabs 9abc to include inferred requirements | 2018-04-19 | NS | N/A
0.4 | changes to requirements tab 9abc after BA review. Removal of Provider update - API version tbc. include new topology. | 2018-05-03 | NS | N/A
Reviewers
This document must be reviewed by the following people:
Reviewer name | Title / Responsibility | Date | Version
Richard Dobson | Assurance Manager
Hadleigh Stollar | NRLS Programme Manager
Will Weatherill | NRLS Technical Workstream Lead
Andy Williams | NRLS Stakeholder Manager
Richard Pugmire | NRLS Digital Delivery Lead
Paul Butterworth | Head of Technical Support Services
Jamil Yunis | Senior Test and Assurance Manager [interoperability; non-functional]
Alan Laithwaite | Test and Assurance Manager [central NRLS service]
Nicola Young | Senior Test and Assurance Manager
Mike Anderson | Test and Assurance Manager [clinical safety]
Mark Thomas | Safety Engineer
cyber security | Security Subject Matter Experts
Stephen Elgar | IG Specialist - Interoperability
Raman Behl | Clinical Specialist NRLS
Chris Squibb | Service Introduction Manager
Gemma Lofthouse | Service BAU Operations
Greg Walker | Service Manager - Service Management
If TOM version changes impact the risks on NHS Digital or Commisioning Organisation, or have a material impact on the process, approval will be sought from the senior approvers.
For minor changes, or changes which have no material impact on the process or risk profile, this will be validated only by the reviewers listed.
Approved by
This document must be approved by the following people:
Name | Title / Responsibility | Date | Version
Debbie Chinn | Director of Solution Assurance
Hadleigh Stollar | NRLS Programme Manager
Requirements Source
The requirements in this document come from the following
Name | Location | Date | Version
Gate 0 solution requirements | NWR-426 - National Record Locator Service | 2018-01-04 | V1.1
NRLS Current Published API Specification | https://developer.nhs.uk/apis/nrls/ |  | NRLS 1.0.0-beta API
NRLS FHIR Structured Definitions | https://fhir.nhs.uk/STU3/StructureDefinition/NRLS-DocumentReference-1 | 2018-02-09 | 1.0.0
NRLS Data Privacy Impact Assessment | NRLS DPIA 20180327 v 04 | 2018-03-27 | 04

## Introduction
NHS Digital NRLS - Target Operating Model (TOM) Self-Evaluation Checklist
CHECKLIST SECTIONS
KEY FOR COMPLETION
| This section captures contact details for all involved organisations. Required for Phase 1A | The colour key used throughout this document is:
NHS Digital to complete
Supplier to complete
End User organisation to complete
| Captures Supplier information. Required for Phase 1A and 1B | Supplier/End User collaborate to complete
Captures Organisation information, data usage, and the associated legal agreements. Required for Phase 1A
Shows the NHS Digital recognised topologies. One must be selected as part of the evaluation process. Required for Phase 1A
This section assesses the technical and integration architecture, and highlights any risks or issues. Required for Phase 2
This section considers the IG implications of the new interface - assessing the Controls in place against the Business Scenario. Required for Phase 2
This section assesses whether there may be clinical safety implications of the new interface. Required for Phase 2
This section ensures the correct Service Management processes are in place to assist the deployment and maintenance once the application is deployed in to the live environment. Required for Phase 2
This section is the assessment o fNRLS applications against the NRLS requirements. Required for Phase 1B
1 - Contact Log
9n - NRLS Reqs
4 - Topology
6 - IG and Security
5 - Architecture
7 - Clinical Safety
2 - Supplier Information
Phase 1A - Usage and Settings submission for approval by NHS Digital
This phase determines if a request to interact with the datasets owned and controlled by NHS Digital is appropriate. The Target Operating Model captures the proposed usage and settings statement (in 3 - End User Organisation tab) for assessment by NHS Digital. The assessment will confirm the legal basis for sharing this data with the End User Organisation and in some cases with the supplier, and establish if a Data Sharing Framework Contract (DSFC) and Data Sharing Agreement (DSA) are required between NHS Digital and the requesting organisation. Following NHS Digital's assessment of the usage and settings information, the Target Operating Model will be returned with the outcome detailed in the 'Approval Gateways' tab.
Please note that to gain approval for this phase, both the End User Organisation and the Supplier need to be IGSoC compliant. Further information on IGSoC compliance can be found here https://digital.nhs.uk/health-social-care-network/new-to-hscn/connecting-to-HSCN
Phase 1B - Technical Conformance for approval by NHS Digital
This phase assesses technical conformance of the product (i.e. the SMS Client) developed by the supplier in line with the requirements. The SMSP guidance explains in detail the requirements in scope, which in summary includes the web service interface requirements, the generic ITK technical requirements , and the specific SMSP requirements specified in tabs 9a and 9b. Technical Conformance assessment involves local testing against an NHS Digital supplied interface stub, followed by end-to-end testing in a live like spine environment. Once these are completed to the satisfactory level NHS Digital will issue a statement of technical conformance in the Approval's tab of the TOM.
Phase 2 - Full TOM and Product evaluation by the End User Organisation
The purpose of this phase is to assist the End User organisation in providing the approval of the TOM and the Service provided by the Supplier. The End User Organisation requesting the spine mini service connection is responsible for ensuring conformance with the guidance in this document as stated in the End User Policy, as this will not be centrally assured by NHS Digital. The End User Organisation requesting the spine mini service connection is responsible for approving the Service evaluation against the TOM and accepting any risks highlighted throughout this document. Any non-conformance with a mandatory (“MUST”) requirement on the tab(s) '9 - SMS Client Reqs' MUST be formally reported to NHS Digital so that the risks to national systems can be assessed. Dependant on the results of this risk assessment, NHS Digital reserves the right to refuse the use of a Spine Mini Services connection.
Note: Phase 2 may be conducted in parallel to phase 1a and 1b to expedite the process, whilst acknowledging a go-live dependency of approval to access central data being granted. Before any deployment can commence, the Supplier MUST sign the Connection Agreement and the End User MUST sign the End User Policy,
In the case of further questions or queries please contact itkconformance@nhs.net.
3 - End User Organisation
8 - Service

## User Guide
Roles and Responsibilities
The table below outlines the roles and responsibilities for those who will either complete, review or approve the Target Operating Model (TOM)
Role | Responsibility within the TOM Completion, Review and Approval Process
End User Organisation | Organisation responsible for the deployment Responsible for completing the relevant sections of the TOM, demonstrating compliance against the requirement set Responsible for providing acceptance of the End Product (Phase 2) Accountable for reviewing the content of the completed TOM and accepting any key risks, exclusions or mitigations (Phase 2) May also be the Supplier, if a Client End Product is being developed in-house Organisation which will be the end user of the NRLS Product
Supplier | Organisation responsible for developing the product which will be used by the end user Responsible for completing the relevant sections of the TOM, demonstrating the compliance against the requirement set
NHS Digital | Responsible for reviewing the relevant sections of the TOM for completion Accountable for ensuring any key risks which stem from non-compliance against the Target Operating Model are highlighted to the End User Organisation Responsible for ensuring guidance is provided to the Supplier and End User Organisation for Target Operating Model completion Provides approval for the Client to be deployed Provides approval for the Personal Demographics Service Data Access Request (through Usage and Settings approval) Provides statement if technical conformance has been achieved
TOM Completion Guidance | Further information is provided on the Health Developer Network
The notes below provide guidance to those who will be completing the TOM:
File naming: when submitting an iteration of the TOM to NHS Digital for review, please format the filename as follows: TOM - End User - ccyymmdd
Prior to completing the TOM, individuals should familiarise themselves with the supporting notes on the Developer Portal (Health Developer Network - link above) and within the “Introduction” tab of this document. Users should also review the Role and Responsibilities box above to identify which role they will play in the completion of the document.
Users should also determine whether the TOM is being completed to achieve Technical Conformance only or both Technical Conformance and Service Assurance. Both will be required to be completed should they wish to proceed to deployment in to the live environment.
Each tab within the TOM is essentially self-contained and covers a different aspect of the assessment process.
Further guidance about the topics can be found within the “Introduction” tab of this workbook and in the Target Operating Model documentation on the Developer Network, which the (End User organisation) approver should refer to, to inform their final approval decision.
It is anticipated that the Client Supplier and End User Organisation will complete the TOM collaboratively, unless the Supplier is only applying to achieve Technical Conformance, where they will complete the relevant tabs independently (see the Introduction tab for guidance)
A response must be provided for every question. Majority of tabs have a list of questions to answer:
Questions with a category of "Info" capture important information but do not actually affect the outcome of the assessment
Questions with a type of "Action" directly affect the outcome of the assessment, and may lead to further actions being required
Questions with a type of "Req" directly affect the outcome of the assessment, and may lead to further actions being required
Cells within each tab have been colour coded to indicate whether a response is to be provided by a Client Supplier (Red Cells), End User Organisation (Green Cells) or NHS Digital (Blue Cells)
At the bottom of tab 6 and 7 are two headings giving the results:
"Additional Information Required" highlights any further documentation that needs to be collated based on answers to the questions
"Additional Stakeholder Involvement" highlights additional stakeholders who need to be involved (e.g. signoffs), based on the answers to the questions
The completed TOM must be submitted to NHS Digital, it must clearly state within the body of the email whether the TOM is to be checked against Technical Conformance deliverables only or both Technical Conformance and Usage and Settings.
Deployment of the Client in to the live environment is not permitted until NHS Digital verifies that both Technical Conformance and Usage and Settings approval activities have been completed

## Approval Gateways
Phase 1A - Usage and Settings - Approved by NHS Digital
This section details the individual who will assess the Usage and Settings information provided within the End User Organisation tab of this Target Operating Model. This assessment will provide basis for granting access to NRLS Data.
The assessement may require further action - please see the Section 'Outcome of Usage and Settings Statement'
| Category | Role | Guidance | Organisation | Name | Job Title | Approval Date
NHS Digital Approver
|  | NRLS Service Information Asset Owner | The NHS Digital NRLS Information Asset Owner with overall accountability for the data. The assessment is for the usage and setting only and not for any other aspect of the TOM.
| Category | Area | Approved/Rejected | Reason |  |  | Date
Approval/Rejection
|  | System Usage | Select
|  | System Setting | Select
|  | Actual Data User Organisation | Select
| Category |  | Detail |  |  |  | Date
Outcome of Usage and Settings Statement
Action
Phase 1B - Technical Conformance - Approved by NHS Digital
This section details the individual who will assess the technical conformance of the supplier product based on the outcome of testing as detailed ?
Technical conformance will provide basis for issuing the Conformance Certificate to the Supplier.
| Category | Role | Guidance | Organisation | Name | Job Title | Approval Date
NHS Digital Approver
|  | ConformanceTeam | The SA conformance Team is responsible for assuring the supplier product development.
|  | Certificate Number | This is the conformance certificate number, for the version of the Suipplier (End Product) indicated on the certificate.
Phase 2 - Target Operating Model Assessment - Approved by the End User Organisation
This section details the individual who will assess the information provided in the entire Target Operating Model. Any risks highlighted during the completion of the TOM are accepted by and will be managed by the Approver of the End User Organisation.
Once the TOM is approved by this approval panel it should be sent to the Supplier to forward to NHS Digital for audit purposes. This approval will be used as basis to proceed with the deployment of the Service.
| Category | Role | Guidance | Organisation | Name | Job Title | Approval Date
End User Organisation Approver
|  | End User Organisation Owner | I am authorised to accept my organisation’s responsibilities as set out in the TOM and End User Policy, having entered into contract with the Supplier, approve use of the Service. I understand the TOM has been provided to assist my organisation in assuring the Service and there may be additional implications and risks to consider prior to acceptance. I confirm my organisation has assured itself and accepts its obligations and responsibilities (and any risks highlighted) as set out in the TOM and End User Policy.
Other individuals as required

## 1-Contact Log
Step 1 - Contacts Log
This section provides a reference list of stakeholders who MAY need to be contacted, as an aid to building a virtual project team.
It allows specific contact details to be recorded for those roles which are relevant - both for day-to-day practical purposes, and as an audit trail of those involved.
(Note that there may be multiple individuals for some stakeholder roles, and extra lines should be inserted as necessary).
| Category | Item | Guidance | Name | Job Title | Email | Telno | Type
End User Organisation's Stakeholders
|  | End User Organisation Owner | The End User Organisations Executive with overall accountability for this assessment and any associated risks |  |  |  |  | Info
|  | Organisation Executive | The End User Organisations Executive with responsibility for the project (if different to above) |  |  |  |  | Info
|  | Lead Contact | The End User Organisation main contact |  |  |  |  | Info
|  | Other Key Contacts | Alternative contacts (as required) |  |  |  |  | Info
|  | Other Key Contacts | Alternative contacts (as required) |  |  |  |  | Info
|  | Other Key Contacts | Alternative contacts (as required) |  |  |  |  | Info
|  | Other Key Contacts | Alternative contacts (as required) |  |  |  |  | Info
|  | Other Key Contacts | Alternative contacts (as required) |  |  |  |  | Info
|  | ICT Manager(s) | ICT Manager for the End User Organisation(s) involved in the project |  |  |  |  | Info
|  | Other key ICT contacts | Other key End User Organisation ICT contacts - e.g. for architecture / design, operations etc. |  |  |  |  | Info
|  | User representative(s) | User representatives - e.g. for requirements and testing activities |  |  |  |  | Info
|  | SIRO(s) | The Senior Information Risk Owner responsible for signoff of IG related risks (Note: May be multiple individuals if several organisations are involved) |  |  |  |  | Info
|  | Clinical Safety Officer(s) | The Clinical Safety Officer responsible for signoff of Clinical Safety related risks as defined by SCCI0160 Standard, mandated by NHS England (Note: May be multiple individuals if several organisations are involved) |  |  |  |  | Info
|  | Clinical Safety Officer(s) | The Clinical Safety Officer responsible for signoff of Clinical Safety related risks as defined by SCCI0160 Standard, mandated by NHS England (Note: May be multiple individuals if several organisations are involved) |  |  |  |  | Info
|  | Clinical Safety Officer(s) | The Clinical Safety Officer responsible for signoff of Clinical Safety related risks as defined by SCCI0160 Standard, mandated by NHS England (Note: May be multiple individuals if several organisations are involved) |  |  |  |  | Info
|  | End User Policy Signatory | The individual that will be the recipient of the End User Policy for a signature |  |  |  |  | Info
Supplier Stakeholders
|  | Supplier | Supplier Name |  |  |  |  | Info
|  | Lead Contact | The Supplier main contact |  |  |  |  | Info
|  | Technical Contact | The technical contact / architect |  |  |  |  | Info
|  |  | Additional contact (as required) |  |  |  |  | Info
|  | Executive Sponsor | The Executive sponsor / escalation point |  |  |  |  | Info
|  |  | Additional contact (as required) |  |  |  |  | Info
|  |  | Additional contact (as required) |  |  |  |  | Info
|  |  | Additional contact (as required) |  |  |  |  | Info
|  |  | Additional contact (as required) |  |  |  |  | Info
|  | Clinical Safety Officer(s) | The Clinical Safety Officer responsible for signoff of Clinical Safety related risks as defined by SCCI0129 Standard, mandated by NHS England (Note: May be multiple individuals if several organisations are involved) |  |  |  |  | Info
|  | Connection Agreement Signatory | The individual that will be the recipient of the Connection Agreement for a signature |  |  |  |  | Info
| Other Supplier's Stakeholders |  | Repeat and add other suppliers as required
|  | Other Supplier 1 | Supplier Name |  |  |  |  | Info
|  | Supplier Lead Contact | The Supplier main contact |  |  |  |  | Info
|  | Supplier Technical | The technical contact / architect |  |  |  |  | Info
|  | Supplier Executive Sponsor | The Executive sponsor / escalation point |  |  |  |  | Info
|  | Clinical Safety Officer(s) | The Clinical Safety Officer responsible for signoff of Clinical Safety related risks as defined by SCCI0129 Standard, mandated by NHS England (Note: May be multiple individuals if several organisations are involved) |  |  |  |  | Info
NHS Digital Stakeholders
|  | NHS Digital Clinical Safety Group contact | Depending on the assessment of clinical safety implications, may need to be used as an advice / escalation point for any Clinical Safety risks. (May be n/a if not involved) |  |  | clinical.safety@hscic.gov.uk |  | Info
|  | NHS Digital Release Manager | Will be used as an advice / escalation point for general impacts |  |  |  |  | Info
|  | NHS Digital Assurance contact | Will advise on conformance in general |  |  | itkconformance@nhs.net |  | Info
|  | Service contact | Will advise on specific details (e.g. training, support) |  |  |  |  | Info
| Other Stakeholders | Other contact details | Any other contacts relevant to the specific project - to be added as necessary |  |  |  |  | Info

## 2 - Supplier
Step 2 - Supplier Information
This section captures basic information about the Supplier and the system using the data.
| Category | Item | Guidance | Response | Type
| System Details |  | This details the Supplier.
|  | Product | The product requesting and receiving data from the NRLS interface |  | Info
|  | Supplier | The supplier of the product |  | Info
|  | Organisation Data Service (ODS) code | A single ODS code of the Supplier - see https://odsportal.hscic.gov.uk/. |  | Action
|  | Is this product being assessed | If the product is already deployed further assessment of this product is not required |  | Info
|  | First of Type | Yes or No. If the system has previously implemented this interface (e.g. at another End User Organisation) it would not be a first of type.If No, indicate organisation name. |  | Info
|  | Version and configuration details | Where known and relevant, provide any further details about the product configuration (e.g. licensed modules, relevant parameter settings etc.) |  | Info
| IG Toolkit Compliance |  | Details of the IG Toolkit compliance status (information can be found on the IG toolkit - https://www.igt.hscic.gov.uk/ )
|  | Current IG Toolkit (IGT) Version | The score quoted below should be using the latest IGT version - an IGT assessment must be completed and published annually |  | Action
|  | Organisation Type | Select best match from list |  | Action
|  | Date Started | Date started IG Toolkit |  | Action
|  | Date Published | Date IG Toolkit was published |  | Action
|  | Self-assessed Grade | IG Toolkit compliance grade; if relevant, provide details in "Response text" |  | Action
| IGSoC Compliance |  | Details of the IGSoC compliance status (for information see - https://digital.nhs.uk/health-social-care-network/new-to-hscn/connecting-to-HSCN#The HSCN Connection Agreement/ )
|  | Organisation Type (if different from IGT Organisation Type) | Select best match from list |  | Action
|  | Start date | Date received IGSoC |  | Action
| Interface Overview |  | This details the actual use and physical storage of the data
|  | Overview description | Provide a brief introductory overview describing at a high level what the interface does and why it is being introduced |  | Action
|  | Data Usage | Provide a description of how the data retrieved from Spine will be used e.g. displayed on a screen with the subject of the data in attendance, a batch job with no user interface. |  | Action
|  | Data Storage | Describe by who and where the data will be held/stored e.g. on End User Organisation servers, on servers belonging to third party suppliers commissioned by an End User Organisation to do work on behalf of the End User Organisation |  | Action
|  | User base | Explain in broad terms who will be using the system (e.g. number of users, typical job roles e.g. social worker, doctor, pharmacist, administrator) |  | Action
|  | Key dates | Outline any key dates relevant to the self-assessment process (e.g. target Go-Live dates) |  | Info

## 3 - End User Organisation
Step 3 - End User Organisation
This section captures basic information about the NRLS access request and is used to determine the application type and approval route.
Cat. | Item | Guidance | Date / List / Code | Response text - or code or list and explanatory text | Assess
Health or Social Care Organisation Details (End User Organisation)
| Organisation Name | Full name required. |  |  | NYA
| Contact Name(s) |  |  |  | NYA
| Contact Postal Address |  |  |  | NYA
| Contact Postcode |  |  |  | NYA
| Contact Email Address |  |  |  | NYA
| Contact Telephone | Direct dial number please. |  |  | NYA
| ODS Code | A single ODS code of the organisation with responsibility for the demographics query event. See https://odsportal.hscic.gov.uk/ - insert code in column D. |  |  | NYA
| Organisation Type | Select best match from list |  |  | NYA
| NHS or not | Select from list. For Mixed and Non-NHS staff explain in "Response" box |  |  | NYA
| Data Controller(s) | Provide role (not name), organisation and address. Definition of a Data Controller can be found https://ico.org.uk/for-organisations/guide-to-data-protection/key-definitions/ |  |  | NYA
| Data Processor(s) | Provide role (not name), organisation and address. Definition of a Data Processor can be found https://ico.org.uk/for-organisations/guide-to-data-protection/key-definitions/ |  |  | NYA
| Date this form first Submitted | Subsequent dates can be in the "Response" box. |  |  | NYA
Data Protection Act Information
| Data Protection Act Registration details | Provide a web link. |  |  | NYA
| Fair Processing Notice (FPN) details | Also known as a Privacy Notice; please provide a web link to your organisation's notice. Must be fully compliant with the guidance of https://ico.org.uk/media/for-organisations/guide-to-data-protection/privacy-notices-transparency-and-control-1-0.pdf and Independent Group Advising on the Release of Data (IGARD). Further information about the IGARD is available here http://content.digital.nhs.uk/IGARD. |  |  | NYA
Existing Data Sharing Framework Contract |  | Must be in place in some instances before the request is approved, typically for non-NHS organisations |  | If a DSFC is required and is not in place, further information will be provided by NHS Digital
| Reference | Insert reference (this may reference the former HSCIC) in column D or state "Pending" or "N/A" in 'Response' box. |  |  | NYA
| Date of Signature by NHS Digital | The effective start date. |  |  | NYA
| Expiry Date |  |  |  | NYA
Existing Data Sharing Agreement (DSA) |  | If more than one - additional information in "Response".
| Reference | Summary of purpose in "Response" box with DSA reference. NB Each purpose will have a separate DSA. If not applicable please state why. |  |  | NYA
| Date of Signature by NHS Digital | The effective start date. |  |  | NYA
| Expiry Date |  |  |  | NYA
Local Data Sharing Agreements
| For multiple local organisations | Provide an overview of the local Data Sharing Agreements and embed documents (if not applicable please state why). |  |  | NYA
PDS Data and Access Method
| PDS data already held | If appropriate. List data items. |  |  | NYA
| Current PDS access method | If appropriate. Select from list. |  |  | NYA
| PDS data requested | List data items. |  |  | NYA
| Requested PDS access method | Select from list. |  |  | NYA
| Application provider name | For Spine Integrated systems and Spine Mini Service Provider (SMSP) only |  |  | NYA
| Registration Authority (RA) and ODS code | For Spine Integrated systems and Summary Care Record Application (SCRa) only. Insert RA ODS Code. |  |  | NYA
Request Details |  | Embed documents as appropriate.
| Processing Objectives and Purpose | Summary information - abstract of the "Method" detail below. |  |  | NYA
| Context Diagram | Describing the player organisations, the data flows between them and the underlying technical architecture. Embed a PDF of a PowerPoint or Visio diagram. |  |  | NYA
| Method: Business Processes | Overview of Use Cases, with reference to the Context Diagram.. |  |  | NYA
| Method: System Processes | With reference to the Technical Architecture. |  |  | NYA
| Outputs | In Business Process terms. |  |  | NYA
| Benefits | To the end users and patients or service users. Provide real life examples if appropriate. |  |  | NYA
User information
| User roles | eg, nurse, care worker. |  |  | NYA
| Numbers of users in each role |  |  |  | NYA
| Target date for implementation |  |  |  | NYA
Legal Basis
| Public bodies - the Statutory Functions | Highlighting those relevant to this request. Embed PDF document. |  |  | NYA
| Legal Basis for data release by NHS Digital | If known at this stage. Embed PDF document. |  |  | NYA
| Health and Social Care Act 2012 ref. | Section, etc. |  |  | NYA
| Legal Basis for data receipt and use | If known at this stage. Embed PDF document. |  |  | NYA
| Relevant Sections of relevant Acts | Acts and Sections, etc. |  |  | NYA
Security and IG Assurance |  | IG Toolkit information available at: https://www.igt.hscic.gov.uk
| Current IG Toolkit (IGT) Version | The score quoted below should be using the latest IGT version - an IGT assessment must be completed and published annually |  |  | NYA
| Organisation Type | Select best match from list
| Date Started | Date started IG Toolkit |  |  | NYA
| Date Published | Date IG Toolkit was published |  |  | NYA
| Self-assessed Grade | IG Toolkit compliance grade; if relevant, provide details in "Response text" |  |  | NYA
| ISO 27001 Certification Details | If certificated against the ISO27001 Information Security standard, insert certificate details (reference, date obtained, scope) or embed a copy of the certificate. |  |  | NYA
| Security Policy Information | Only needed if there is no current/valid IGT score and no ISO 27001 - seek advice from demographics@nhs.net. Embed PDF documents as necessary. |  |  | NYA
| Data Centre Location(s) - Main | Full address. |  |  | NYA
| Jurisdiction | Select from list. If "other" provide full details. | England / Wales |  | NYA
|  | Additional jurisdiction information, if appropriate. |  |  | NYA
| Data Centre Location(s) - Backup | Full address. |  |  | NYA
| Jurisdiction | Select from list. If "other" provide full details. | England / Wales |  | NYA
|  | Additional jurisdiction information, if appropriate. |  |  | NYA
| Territory of Use Jurisdiction | Select from list. If "other" provide full details. | England / Wales |  | NYA
|  | Additional jurisdiction information, if appropriate. |  |  | NYA
Deploying Health or Social Care (End User) Organisation IGSoC status - N3 / HSCN connections |  | Details of the IGSoC compliance status For information see https://digital.nhs.uk/health-social-care-network/new-to-hscn/connecting-to-HSCN#The HSCN Connection Agreement/
| Organisation Type (if different from IGT Organisation Type) | Select best match from list |  |  | NYA
| Start date | Date received IGSoC |  |  | NYA
Other Supplier Details |  | For all other products involved in the end to end system |  | Enter 'N/A' if none
| Product(s) | The product name(s). Refer to Context Diagram and Technical Architecture. |  |  | NYA
| Supplier(s) | The supplier(s) of the product(s). |  |  | NYA
| Has product already been technically assessed? | Common Assurance Process (CAP) for Spine Integration or Interoperability Toolkit (ITK) conformance |  |  | NYA
| Purpose | Describe the role this product plays in the deployment scenario. Refer to Context Diagram and Technical Architecture. |  |  | NYA
| First of Type | Has this supplier implemented this interface before (eg, at another health or care Organisation)? |  |  | NYA
| Version and configuration details | Where known and relevant, provide any further details about the product configuration (eg, licensed modules, relevant parameter settings. etc). |  |  | NYA
| Service aggregation information | If this is a service provided to more than one organisation, give an overview of the service. Refer to Context Diagram and Technical Architecture. Note that separate agreements may be required for each organisation receiving the service. |  |  | NYA

## 4 - Topology
Step 4 - Please Select the Topology which matches the Deployment
Topology Number
Selected Topology
| Category | Item | Guidance | Response | Type
| Supporting Topology Information |  | This details key information about the Supplier Topology
|  | Topology Justification | Provide an outline for how the application meets the selected system topology. |  | Action
|  | No. of End Points | Outline how many End Points are going to be used for the deployment (i.e. single end point or multiple end points per deployment) |  | Action
|  | End Point Registration | Is the intention to use existing live end points or use new end points. If existing End Points are to be used confirm the relevant details here (inc ASID) |  | Action
|  | Data storage | Is the data persistent in the Supplier's system and can be accessed by the Supplier as well as the End User Organisation? |  | Action

## 5 - Architecture
Step 5 - Architecture
This section examines the system architecture to ensure that it is fit for purpose.
It provides best-practice guidance which End User Organisations must consider when assuring their own architectures.
The intention is for this spreadsheet to act as a checklist and cross-reference to ensure that all necessary points are covered in more detailed technical documentation.
| Category | Item | Guidance | Action By | Additional Notes / References | Type
IT Operations Planning
| IO-01 | Data Centre Resilience and Manageability | Ensuring that consideration is given to hosting the solution with an appropriate level of resilience and reliability. Topics to cover include: - Resilience / Failover - Identification of any single points of failure - Load balancing design and failure scenarios - Backup and Recovery - Disaster Recovery - Alerting and Monitoring | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info
| IO-02 | Go Live planning | Ensuring that the Go Live process is adequately planned, including contingency planning. Topics to cover include: - Cutover and Fallback - Installation and Configuration - Network worthiness - Data Migration | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info
| IO-03 | Operational Checks | Planning for checks that the system is operating correctly Topics to cover include: - Audit - Journaling - Usability | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info
| IO-04 | End-to-End Performance Design Review | Ensuring that the solution is performant under the anticipated usage load. Topics to cover include: - Estimated usage volumetrics - Service Levels required - End-to-end performance implications of transactions via the new interface. - Volume and Performance (V&P) testing and / or performance design review | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info
Integration Architecture
| IA-01 | Integration Architecture | Ensuring that an appropriate integration architecture is in place. Topics to cover include: - Use of integration middleware (e.g. Trust Integration Engine, Toolkit Middleware) - Interface usage (Can existing interfaces be used and/or are any new interfaces or messages needed?) - Adapters (Consideration of any new adapters that may be needed to convert between data formats) - End-to-End Reliability (e.g. acknowledgements, retries, transactionality) - Sequencing (Mechanisms used to manage business and technical level sequencing and orchestration of messages) - Backwards and Forwards compatibility (The technical approach to message versioning, and the approach to handling potential changes in the message definitions) | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info
| IA-02 | Interface Change Planning | Ensuring that the processes and procedures in place to make sure that the interface can be maintained and kept up-to-date. For example, what would be the impact of a change to an upstream system, and how would this be notified and managed? This is likely to include regression testing | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info
Information Architecture
| IN-01 | Data Quality review | Ensuring that the solution supports data quality - and in particular that the new interface does not propagate low quality or misleading data between systems. Topics to cover include: - Message validation (The approach to technical message validation - specifically how sending systems ensure that generated messages are valid) - Data content quality (The mechanisms in place to ensure that data passing via the new interface is complete, consistent, timely and accurate) - Data Concurrency (Ensuring that data made available via the new interface is kept up-to-date, and that updates of "stale" data are not able to corrupt upstream system) | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info
| IN-02 | Use of Data Standards | Ensuring that the solution makes appropriate use of all relevant data standards. Topics to cover include: - Use of NHS Digital Data Standards including: • SNOMED – for reference terminology • NHS Data Dictionary – for administrative codes • ICD-10 and OPCS – for reporting - Reasons for any differences from the above. - Does the project represent an opportunity to migrate towards these NHS Digital data standards? - Data Mappings (Are any mappings between different data standards required? If yes, indicate what these mappings are - and confirm that it is both possible and clinically safe to perform the translation) | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info
Clinical Safety
| CL-01 | Technical Clinical Safety Review | Ensuring that the technical aspects of the solution provide adequate support for clinical safety Topics to cover include: - What is the impact on care or provision of clinical of any integration layer becoming unavailable? - What is the impact of a transactional failure, or a failure of a single request in a sequence of interactions ? - Are there any implications for “chains of systems” – such that changes to one system have clinical safety implications for other systems with which it is integrated? - How are users informed of a failure so that they can react accordingly ? - How are applications informed of a failure to that they can support their users, and leave their systems in a safe, stable state ? - How are failures logged so that operations staff can understand what went wrong, and react accordingly ? | To be completed by the Supplier to provide best-practice guidance to the End User Organisation |  | Info

## 6 - IG and Security
Step 6- Information Governance and Security
This section confirms the Information Governance (IG) controls required, and the mechanisms for implementation of each.
The emphasis is on highlighting the business requirement for a particular control, rather than mandating that a particular technical mechanism be used.
For each IG control a number of recognised technical implementation mechanisms are listed, and use of these pre-established mechanisms can accelerate implementation.
Where a non-standard technical implementation mechanism is proposed then the checklist will highlight the need for further review and risk assessment by the End User Organisation's Senior Information Risk Owner (SIRO).
This IG checklist applies to generic components. It should be noted there exists additional NRLS specific IG requirements detailed in tabs 9a, 9b and 9c.
| Category | Control | Guidance | Actioned By | Compliance | Additional Notes / References | Type
| Business Scenario(s) |  | The TOM IG guidance contains a number of business scenarios, each requiring different levels of IG controls. | Actioned by | Compliance | Additional Notes/References
|  | NRLS Search | NRLS pointer is queried under the control of the consuming system | …...on behalf of the Supplier |  |  | Action
|  | NRLS Create | NRLS pointer is created under the control of the proving system | …...on behalf of the Supplier |  |  | Action
| Process Controls |  | These Process Controls are always relevant |  | PASS |  | MUST
|  | Information Security Management System (ISMS) | Is a formal Information Security Management System in place? An Information Security Management System (ISMS) is defined as that part of the overall management system, based on a business risk approach, to establish, implement, operate, monitor, review, maintain and improve information security. BS EN ISO/IEC 27001:2017 is the relevant standard | …...on behalf of the End User Organisation |  |  | Action
| Technical Controls |  | These Technical Controls are always relevant |  | PASS |  | MUST
|  | Secure Communications | Are the requirements for secure communications met? For example, encrypting data in transit All data in transit must be encrypted using an approved cipher suite, in this instance TLS1.2. See approved Cryptographic Algorithms Document http://webarchive.nationalarchives.gov.uk/20161101131024/http://systems.digital.nhs.uk/infogov/security/infrasec/gpg | …...on behalf of the Supplier |  |  | Action
|  | Storage | Are there adequate controls of data in storage? For example are storage devices encrypted and / or located in a secure area? See approved Cryptographic Algorithms Document http://webarchive.nationalarchives.gov.uk/20161101131024/http://systems.digital.nhs.uk/infogov/security/infrasec/gpg | …...on behalf of the Supplier |  |  | Action
|  | Time Stamping | Is an accurate time source in place? Date and time between systems (e.g. for use in audit logs) should be synchronised within 250 milliseconds of the NASP-provided or National Network Time Servers | …...on behalf of the Supplier |  |  | Action
|  | Network Access | Are the guidelines for network access controls met? See https://nww.carecertisp.digital.nhs.uk/display/CC/NHS+Digital+Good+Practice+Guides 'Access Control Lists'/'Firewall Technologies'/'LAN Security' | …...on behalf of the Supplier |  |  | Action
|  | Workstation Access | Are workstations and servers adequately secured? See referenced guidance from the National Institutes of Standards Technology (NIST) for more details | …...on behalf of the Supplier |  |  | Action
|  | Content Commitment | Are Digital Signatures used where necessary to sign content and / or authenticate the identity of a sender? This may be not applicable, in which case leave blank and note as "Not applicable" in the Additional Notes column | …...on behalf of the Supplier |  |  | Action
|  | Security Testing | Has a penetration test been completed and an action plan been developed to mitigate any vulnerabilities identified? | …...on behalf of the End User Organisation …...on behalf of the Supplier |  |  | Action
| IG Controls (Baseline) |  | These Baseline IG controls are always relevant |  | PASS |  | MUST
|  | Authentication | What mechanism is provided for secure authentication of users? Recognised authentication (log-on) mechanisms include: - Spine smartcard - Other strong authentication e.g. two-factor token logon Other mechanisms (e.g. username and password )should be noted as "Other" and described further in Additional Notes. | …...on behalf of the Supplier |  |  | Action
|  | Role Based Access Control (RBAC) | What access control approach is implemented? Role Based Access Control should limit users so that they can only access system functionality relevant to their job role Recognised mechanisms include both National and Local RBAC If Local RBAC is selected, please provide further details (this may be in the form of a reference to additional documentation) Other mechanisms (e.g. limiting physical access to the system )should be noted as "Other" and described further in Additional Notes. | …...on behalf of the Supplier |  |  | Action
|  | Audit | Is a full audit trail provided? | …...on behalf of the Supplier |  |  | Action
|  | Data Retention | Is data retention provided, in line with NHS retention standards? See https://digital.nhs.uk/codes-of-practice-handling-information for more details of minimum retention periods for different data types | …...on behalf of the Supplier |  |  | Action
| End-to-End Information Flows |  | This section looks at the overall end-to-end information flows and examines the potential for data leakage or data integrity issues as a result of implementing the new interface |  | PASS |  | MUST
|  | End-to-End Information Flows | Provide reference to documentation (e.g. diagram) showing the information flows to / from the system being assessed and other systems in the estate. Specifically, the purpose is to highlight: i) The potential ultimate destinations of any patient identifiable Spine-originated data passing through this system ii) The potential original sources of any data updates made to Spine via this system | …...on behalf of the End User Organisation …...on behalf of the Supplier |  |  | Info
|  | Data Leakage Issues? | Are there any downstream systems which have not passed this self-assessment process, and to which this system passes patient-identifiable Spine originated data? If "yes", please provide details in Additional Notes | …...on behalf of the End User Organisation …...on behalf of the Supplier |  |  | Action
|  | Data Integrity Issues? | Are there any downstream systems which have not passed this self-assessment process, and which act as a source of data for this system to update a Spine Compliant system? If "yes", please provide details in Additional Notes | …...on behalf of the End User Organisation …...on behalf of the Supplier |  |  | Action
| Downstream Issue Business Scenario(s) |  | If the analysis of End-to-End Information Flows above has identified further systems downstream of the new interface itself, indicate the nature of these further data flows (This has implications for the significance of any data leakage or data integrity issues identified)
|  | Demographic Query | Demographic data is queried under the control of the receiving system | …...on behalf of the Supplier |  |  | Action
|  | Demographic Cross Organisation | Demographic data is transmitted across organisational (e.g. Trust) boundaries. Any cross-organisation data flow has appropriate authorisation and data sharing agreements in place. | …...on behalf of the End User Organisation |  |  | Action
| External Impacts |  | Are there any potential implications or risks of this work for external organisations?
|  | Other Health Organisations impacted? | Could this interface potentially have an impact on data belonging to other Health Organisations? (e.g. shared PAS instance) | …...on behalf of the End User Organisation |  |  | Action
|  | Spine impacted? | Could this interface potentially have an impact on Spine data? | …...on behalf of the End User Organisation …...on behalf of the Supplier |  |  | Action
Additional Information Required
Additional Stakeholder Involvement
SIRO - This IG assessment must be submitted to the End User Organisation's Senior Information Risk Owner for sign-off

## 7 - Clinical Safety
Step 7 - Clinical Safety
This section confirms actions required to mitigate Clinical Safety risks.
Dependant on the clinical setting of your Health IT system, this section must be completed or have input from either; - a Clinical Safety Officer or suitably trained and experienced clinicians - a Social Care Professional, registered by the General Social Care Council and MUST be signed off as indicated in the Additional Stakeholder Involvement section below.
Clinical safety signoff requirements are determined below on completing questions 1 to 5, there are five possible outcomes; 1. None Required 2. Local Only (Non Clinical) 3. Local Only (Clinical Safety Related) SCCI0129 / SCCI0160 needs to be applied 4. NHS Digital Clinical Safety Group Assistance Required 5. The System falls under the category of a Medical Device and guidance should be sought from the MHRA If further guidance is needed then the NHS Digital Clinical Safety Group may be contacted on clinical.safety@nhs.net
| Category | Item | Guidance | Actioned By | Compliance | Additional Notes / References | Type
Clinical Safety
| CS-01 | Medical Device? | Q1 Is your system a Medical Device or eligible to be a Medical Device? Output: If the answer is ‘No’ further safety assurance work may be required. Continue to Q2 If the answer is ‘Yes’ the system falls under the category of a medical device and guidance should be sought from the MHRA. | …...on behalf of the End User Organisation |  |  | Action
| CS-02 | Updating Spine? | Q2 Is the System updating data held on the Spine? Output: If the answer is ‘Yes’, further safety assurance may be required in accordance with SCCI0129 / 0160 | …...on behalf of the End User Organisation |  |  | Action
| CS-031 | System Function? Is there a requirement on Clinical Safety? | Q3.1: Is the System integrating with other systems (e.g. a parent System, examples may include a patient administration system or prescribing system)? Output: If the answer is ‘Yes’, further safety assurance may be required in accordance with SCCI0129 / SCCI0160. | …...on behalf of the End User Organisation |  |  | Action
| CS-032 |  | Q3.2 Is the system used solely to automate general office functions to assist in payments and billing etc.? | …...on behalf of the End User Organisation |  |  | Action
| CS-033 |  | Q3.3 Is the System a transactional one (e.g. Used to book, amend and cancel appointments or to issue a prescription or repeat medication)? Output: If the answer is ‘Yes’, further safety assurance may be required. | …...on behalf of the End User Organisation |  |  | Action
| CS-034 |  | Q3.4 Is this a calculation and / or monitoring System (e.g. recording patient Clinical Information), which is used to record, track and/or maintain health for ongoing Clinical support? Output: If the answer is ‘Yes’, further safety assurance may be required in accordance. | …...on behalf of the End User Organisation |  |  | Action
| CS-04 | Safety Issues? | Q4 Were any clinical safety issues identified by the technical clinical safety review performed in the "Architecture CL-01" section of this checklist? | …...on behalf of the End User Organisation |  |  | Action
| CS-051 | Safety Compliance | Q5.1 As the client and where a Hazard log is provided by NHS Digital have you: a) reviewed the Hazard log? b) implemented appropriate local mitigations? c) transferred the Hazards/Mitigations into the local business processes and accepted ownership of residual risk(s)? | …...on behalf of the End User Organisation |  |  | Action
| CS-052 |  | Q5.2 In applying the questions set out in Q2 through Q3, does the output recommend further safety assurance as required under SCCI0129 or 0160? | …...on behalf of the End User Organisation
| CS-053 |  | Q5.3 As the client, have you conducted a formal Risk Assessment and identified Clinical Safety Hazards in accordance with SCCI0129 / 0160? | …...on behalf of the End User Organisation |  |  | Action
| CS-054 |  | Q5.4 As the client, is there a formal Safety Case and incorporating Hazard log? | …...on behalf of the End User Organisation |  |  | Action
| CS-055 |  | Q5.5 As the client, is there: a) a Clinical Safety Officer or suitably trained and experienced clinicians or b) a Social Care Professional, registered by the General Social Care Council. who has signed off the system and interface? | …...on behalf of the End User Organisation |  |  | Action
| Clinical Safety Signoff Level | 1 - None Required | See Clinical Risk Management standards and implementation guidance documents for details http://systems.digital.nhs.uk/clinsafety
Additional Information Required
Additional Stakeholder Involvement

## 8 - Service
Step 8 - Service Readiness
This section ensures the correct operational processes are in place.
The information is to be submitted by the Supplier however it is anticipated input will be required from the End User Organisation to answer SR-12.
Submitted information will be recorded by the NHS Digital Service Management team.
It is the responsibility of the End User Organisation to agree the specific deployment approach with the Supplier
| Category | Activity | Activity Description / Help Text | Compliance Level | Evidence | Comments | Type
Client Supplier
| SR-01 | Client Supplier Service Desk contact number | Telephone number for operational contact regarding the service. |  |  |  | Action
| SR-02 | Client Supplier Service desk email address | Primary email address. |  |  |  | Action
| SR-03 | Support Hours | State the hours of support provided by the Client Supplier Service Desk. |  |  |  | Action
| SR-04 | NHS Digital National Service Desk | Confirm that the Supplier has registered with the SSD National Service Desk. Guidance is available here https://nww.nhscfhservicedesk.nhs.uk/NSD/servlet/NSDHelp |  |  |  | Action
| SR-05 | Out of hours contact number (state if same as above) | If there is an on-call rota, please advise how this will be provided to the NHS Digital Service Bridge. (servicebridge@nhs.net) |  |  |  | Action
| SR-06 | Operational contact numbers | Please provide local organisation chart where possible, with the roles pertaining to this service explained. |  |  |  | Action
| SR-07 | Incident Management | Confirm that the Supplier has an incident management process in place that it will use with Commissioning Organisations and that is consistent with the NHS Digital Incident Management process. Attach evidence of any service and incident management processes to be used. |  |  |  | Action
| SR-08 | Incident Severity Levels | Please provide the incident severity levels that you will apply for this service with associated guidance on usage. Please indicate SLA response times for all incident severity types. E.g. Severity Level 1 (Critical): HSSI Severity Level 2 (High): HSSI Severity Level 3 (Medium) Severity Level 4 (Low) Severity Level 5 (Very Low) |  |  |  | Action
| SR-09 | High Severity Service Incident Manager | Please provide either a name or the rota for performing this function. If the named contact/s will change regularly, please advise how the updated details will be provided to the NHS Digital Service Bridge. |  |  |  | Action
| SR-10 | Escalation and Complaints Process | Please provide the escalation process for this service. Further guidance is included below*. |  |  |  | Action
| SR-11 | Escalation Contacts (all relevant levels) | Name, email and phone numbers of all escalation contacts with the escalation level associated with each contact. |  |  |  | Action
| SR-12 | Anticipated Go Live date for the service with Commissioning Organisation users | If the Go-Live will be phased then anticipated dates and timeframes for the service to be introduced with end users. |  |  |  | Action
End User Organisation
| SR-13 | Operational contacts and contact details (phone, email) | Please provide local organisation chart where possible, with the roles pertaining to this service explained. |  |  |  | Action
| SR-14 | Escalation and Complaints Process | Please provide the escalation process for this service. Further guidance is included below*. |  |  |  | Action
| SR-15 | Escalation Contacts (all relevant levels) | Name, email and phone numbers of all escalation contacts with the escalation level associated with each contact. |  |  |  | Action
| SR-16 | Anticipated Go Live date for the service with Commissioning Organisation users | If the Go-Live will be phased then anticipated dates and timeframes for the service to be introduced with end users. |  |  |  | Action
* GUIDANCE The escalation and complaints process shall comply with the following principles: - The party raising the Escalation or Complaint shall be kept informed of progress at an appropriate interval as agreed with the party raising the Escalation - All Escalations and Complaints shall be managed to an appropriate conclusion with agreed remedial actions to prevent re-occurrence - Escalations and Complaints shall not be closed without the agreement of the party that raised them - Details of all Escalations and Complaints shall be retained on the audit trail for a period of two years - Activity should be undertaken by the party against whom the Complaint was made in order to minimise the re-occurrence of the issues underlying reported Escalations and Complaints.

## 9a - Supplier Reqs
Step 9a - Supplier Requirements
This section assesses the application against the published set of NRLS Requirements.
Any required actions will appear beneath the main table, depending how the Compliance Status column is populated.
| Category / Requirement | Item | Detail | Guidance | Type | Actioned By | Compliance Status | Additional Notes / References | Type
; | General IG
| S1 | DPIA conformance | have you read in understood your obligations described in the NRLS DPIA link: | Statement | Must | …...on behalf of the Supplier |  |  | Req
Static Validation
| S2 | Test Tool validation | Security (SSL), Including the supported cipher suites | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S3 |  | HTTP custom headers | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S4 |  | Java Web Token (JWT) claims | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S5 |  | FHIR Static Content Validation - FHIR Base and NRLS Profiles | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Business Validation
Comsumer Search
| S6 | Search (using HTTP GET) Document Reference Tests | GET via ODS code | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S7 |  | GET via Patient | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S8 |  | GET via Patient and ODS code | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S9 |  | GET via a parameter and a return code value | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Comsumer Search Responses
| S10 | Search Response Handling Tests | HTTP200 Success Bundle of type DocumentReference returned | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S11 |  | HTTP200 Success Bundle with 0 content | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S12 |  | HTTP403 Access Denied + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S13 |  | HTTP400 Invalid Parameter + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S14 |  | HTTP400 Missing or Invalid Header + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Provider Search
| S15 | Search (using HTTP GET) Document Reference Tests | GET via ODS code | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S16 |  | GET via Patient | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S17 |  | GET via Patient and ODS code | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S18 |  | GET via a parameter and a return code value | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Provider Search Responses
| S19 | Search Response Handling Tests | HTTP200 Success Bundle of type DocumentReference returned | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S20 |  | HTTP200 Success Bundle with 0 content | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S21 |  | HTTP403 Access Denied + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S22 |  | HTTP400 Invalid Parameter + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S23 |  | HTTP400 Missing or Invalid Header + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Provider Create
| S24 | Create (using HTTP POST) Document Reference Tests | POST valid DocumentReference resource for all pointers (direct / indirect) support | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Provider Create Responses
| S25 | Create Response Handling Tests | HTTP201 Success including logicalId and initial versionId | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S26 |  | HTTP403 Access Denied + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S27 |  | HTTP400 Invalid Resource + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S28 |  | HTTP400 Message Not Well Formed + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S29 |  | HTTP400 Missing or Invalid Header + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Provider Delete
| S37 | Delete (using HTTP DELETE) Document Reference Tests | DELETE valid DocumentReference resource, including Id | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Provider Delete Responses
| S38 | Delete Response Handling Tests | HTTP200 Success with ETag header containing the incremented versionId, and Last-Modified header in UTC | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S39 |  | HTTP204 OK | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S40 |  | HTTP404 No Record Found + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S41 |  | HTTP403 Access Denied + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| S42 |  | HTTP400 Invalid Resource + OperationOutcome resource | Evidence | Must | …...on behalf of the Supplier |  |  | Req
Additional Requirements
| NRLS-REQ-F003 | Consumer Supplier | As an NRLS Consumer I am able to filter and sort search results so that I can more easily find the most relevant pointer from within the results | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| NRLS-REQ-F010 | Provider Supplier | As an authorised NRLS Provider/Publisher I am able to access the NRLS service so that I can search and maintain Health Record Pointers from a variety of different locations. | Evidence | Must | …...on behalf of the Supplier |  |  | Req
| NRLS-REQ-F030 | Consumer and Provider Supplier | As an NRLS consumer or Provider I want obtain verified NHS number for the presenting patient so that I can be sure that the NHS number is valid and relates to the correct patient; thus ensuring that it can be effectively found by consumers and providers | Statement | Must | …...on behalf of the Supplier |  | Placeholder: more work will be needed to define this and what options are available for Providers | Req
General Non-Functional
| NRLS-REQ-NF010.05 | Consumer Supplier | As an NRLS Consumer I want an audit log to be maintained of pointers that I have retrieved so that I am able to investigate, explain and justify clinical decisions made where the NRLS has been used and also to investigate claims that pointers have been accessed inappropriately | Evidence and Statement | Must | …...on behalf of the Supplier |  | Placeholder: more work will be needed to define this | Req
| NRLS-REQ-NF010.06 | Provider Supplier | As an NRLS Provider I want an audit log to be maintained of pointers that I have created and deleted so that I am able to investigate, explain and justify the information that I have made available about my patients through the NRLS | Evidence and Statement | Must | …...on behalf of the Supplier |  | Placeholder: more work will be needed to define this | Req
| NRLS-REQ-NF010.07 | Consumer and Provider Supplier | The Publishing or Consuming Supplier system shall comply with the Audit requiremients in NHS Digital IG Audit & Alerts Standards V3.0 | Evidence and Statement | Must | …...on behalf of the Supplier |  |  | Req
Information Governance
| 4.4.3.6 | Consumer Supplier Patient record accessed by end users without appropriate authorisation | Consuming organisations systems must incorporate appropriate User Authentication and Authorisation controls either compliant with national RBAC requirements, or local equivalent NRLS will align where possible to other solutions being developed, for example the Strategic Authentication programme. | Consuming organisations systems must incorporate appropriate User Authentication and Authorisation controls either compliant with national RBAC requirements, or local equivalent NRLS will align where possible to other solutions being developed, for example the Strategic Authentication programme. Consuming organisation commit to use of patient event information within acceptable access control functions Evidence and Statement | Must | …...on behalf of the End User organisation |  |  | Req
Additional Stakeholder Involvement
Self-Evalution Checklist should be submitted to NHS Digital for Audit purposes
Yes
No
Partial
N/A

## 9b - Provider Reqs
Step 9b - Provider Requirements
This section assesses the application against the published set of NRLS Provder Requirements.
Any required actions will appear beneath the main table, depending how the Compliance Status column is populated.
| Category / Requirement | Item | Detail | Guidance | Type | Actioned By | Compliance Status | Additional Notes / References | Type
General
| P1 | DPIA conformance | have you read in understood your obligations described in the NRLS DPIA link: | Statement | Must | …...on behalf of the End User organisation |  |  | Req
Read
| P2 | Review supplier self-certified evidence | Review of any supplier self-certified evidence stated as requiring local organisation acceptance, due to it not be suitable for one-off central NHS Digital assurance. | Statement | Must | …...on behalf of the End User organisation |  |  | Req
Search
| P3 | Review supplier self-certified evidence | Review of any supplier self-certified evidence stated as requiring local organisation acceptance, due to it not be suitable for one-off central NHS Digital assurance. | Statement | Must | …...on behalf of the End User organisation |  |  | Req
Create
| P4 | Review supplier self-certified evidence | Review of any supplier self-certified evidence stated as requiring local organisation acceptance, due to it not be suitable for one-off central NHS Digital assurance. | Statement | Must | …...on behalf of the End User organisation |  |  | Req
Delete
| P6 | Review supplier self-certified evidence | Review of any supplier self-certified evidence stated as requiring local organisation acceptance, due to it not be suitable for one-off central NHS Digital assurance. | Statement | Must | …...on behalf of the End User organisation |  |  | Req
Additional requirements
| NRLS-REQ-F020 |  | As the NRLS I am able to be managed in accordance with Data Sharing Agreement requirements as set out by the Information Governance Alliance (IGA) so that users are correctly operating the service. | Statement | Must | …...on behalf of the End User organisation |  |  | Req
| NRLS-REQ-F030 | Verification of NHS number | As an NRLS Provider I want verifty the NHS number of a patient I am creating a pointer for so that I can be sure that the NHS number is valid and relates to the correct patient; thus ensuring that it can be effectively found by consumers | Statement | Must | …...on behalf of the End User organisation |  | Placeholder: more work will be needed to define this and what options are available for Providers | Req
Information Governance
| 4.4.3.1 | Patients unaware that their data may be shared using NRLS for their direct care | As part of the “on boarding” processes, participating publishing and consuming organisations will be required to notify their patients of the information sharing potential and the constraints within which this will take place | The publishing and consuming organisations will be required to confirm these activities to NHS Digital Solutions Assurance as part of the deployment authorisation` The exact methods, content, and extent of the notification to patients to be confirmed following consultation Statement | Must | …...on behalf of the End User organisation |  |  | Req
| 4.4.3.6 | Patient record accessed by end users without appropriate authorisation | Consuming organisations systems must incorporate appropriate User Authentication and Authorisation controls either compliant with national RBAC requirements, or local equivalent NRLS will align where possible to other solutions being developed, for example the Strategic Authentication programme. | Consuming organisations systems must incorporate appropriate User Authentication and Authorisation controls either compliant with national RBAC requirements, or local equivalent NRLS will align where possible to other solutions being developed, for example the Strategic Authentication programme. Consuming organisation commit to use of patient event information within acceptable access control functions Statement | Must | …...on behalf of the End User organisation |  | . | Req
| 4.4.3.7 | Patient record-sharing dissent overridden | NRLS guidance incorporated into the TOM specifies patient preference for sharing is managed by the publishing organisation. Implied Consent The publishing organisation will pass patient event information if explicit dissent is not recorded, and within the context of a Data-Sharing Agreement held between the NHS Digital and all publishing and consuming organisations. | Publishing organisations commit to use of appropriate preference for sharing functions Statement | Must | …...on behalf of the End User organisation |  |  | Req
| 4.4.3.8 | Patient record section privacy settings overridden | The publishing organisation must respect any patient event information which has been marked as not to be shared. This may take two forms: - not creating a pointer where a patient has stated that they do not want their health record to be shared - removing a pointer where a patient has stated that they do not want their health record to be shared after a pointer has already been created. | Publishing organisations commit to use of appropriate preference for sharing functions Statement | Must | …...on behalf of the End User organisation |  |  | Req
Additional Stakeholder Involvement
Self-Evalution Checklist should be submitted to NHS Digital for Audit purposes
Yes
No
Partial
N/A

## 9c - Consumer Reqs
Step 9c - Consumer Requirements
This section assesses the application against the published set of NRLS Provder Requirements.
Any required actions will appear beneath the main table, depending how the Compliance Status column is populated.
| Category / Requirement | Item | Detail | Guidance | Type | Actioned By | Compliance Status | Additional Notes / References | Type
General
| C1 | DPIA conformance | have you read in understood your obligations described in the NRLS DPIA link: | Statement | Must | …...on behalf of the End User organisation |  |  | Req
Read
| C2 | Review supplier self-certified evidence | Review of any supplier self-certified evidence stated as requiring local organisation acceptance, due to it not be suitable for one-off central NHS Digital assurance. | Statement | Must | …...on behalf of the End User organisation |  |  | Req
Search
| C3 | Review supplier self-certified evidence | Review of any supplier self-certified evidence stated as requiring local organisation acceptance, due to it not be suitable for one-off central NHS Digital assurance. | Statement | Must | …...on behalf of the End User organisation |  |  | Req
General Functional
| NRLS-REQ-F020 |  | As the NRLS I am able to be managed in accordance with Data Sharing Agreement requirements as set out by the Information Governance Alliance (IGA) so that users are correctly operating the service. | Statement | Must | …...on behalf of the End User organisation |  |  | Req
| NRLS-REQ-F031 | Verification of NHS number | As an NRLS Consumer I want to verify the NHS number of the patient that I am searching for so that I do not inadvertently view pointers for the incorrect patient | Statement | Must | …...on behalf of the End User organisation |  | Placeholder: more work will be needed to define this and what options are available for Consumers | Req
Information Governance
| 4.4.3.2 | Patient identifiable and confidential information used for purposes other than direct care | Consuming organisation commit to use patient event information for direct care purposes only | organisations will need, to define Usage and Settings (as part of this document) for approval by NHS Digital and publishing and consuming organisation Information Asset Owners Statement | Must | …...on behalf of the End User organisation |  |  | Req
| 4.4.3.3 | Patient identifiable and confidential information used for unassured use cases/clinical settings within direct care | Consuming organisation commit to use patient event information for assured use cases/clinical settings within direct care | Consuming organisation commit to use patient event information for assured use cases/clinical settings within direct care Statement | Must | …...on behalf of the End User organisation |  |  | Req
| 4.4.3.5 | Patient record accessed by consumer systems without the necessary security framework | Consuming organisation and systems must be NHS IG Toolkit compliant, and meet national requirements for Technical (Endpoint) Security see 3 - End User Organisation : ISO 27001 Certification Details | Consuming organisation commit to use of patient event information within acceptable access control functions Statement | Must | …...on behalf of the End User organisation |  |  | Req
| 4.4.3.6 | Patient record accessed by end users without appropriate authorisation | Consuming organisations systems must incorporate appropriate User Authentication and Authorisation controls either compliant with national RBAC requirements, or local equivalent NRLS will align where possible to other solutions being developed, for example the Strategic Authentication programme. | Consuming organisations systems must incorporate appropriate User Authentication and Authorisation controls either compliant with national RBAC requirements, or local equivalent NRLS will align where possible to other solutions being developed, for example the Strategic Authentication programme. Consuming organisation commit to use of patient event information within acceptable access control functions Statement | Must | …...on behalf of the End User organisation |  | . | Req
Additional Stakeholder Involvement
Self-Evalution Checklist should be submitted to NHS Digital for Audit purposes
Yes
No
Partial
N/A

## 9d - Test Cases
Step 9d - Test Cases
test cases when writtten go on this tab
final test report goes on this tab after tests are executed

## NHS Digital Assessement
NHS Digital use only
NHS Digital PDS IG Scrutiny Organisation Assessment - print on A4
IG Assessment |  | DRAFT v1 |  |  | "Type" column not yet in use - see "Lists" tab for Categories
Cat. | Item | Responses | Assess | Assessment text | Type
Health or Social Care Organisation Details
| NIC | #REF! | NYA |  | #REF!
| Organisation Name |  | NYA |  | NYA
| Contact Name |  | NYA |  | NYA
| Postal Address |  | NYA |  | NYA
| Postcode |  | NYA |  | NYA
| Email Address |  | NYA |  | NYA
| Telephone |  | NYA |  | NYA
| ODS Code | 0 | NYA |  | NYA
| Organisation Type | 0 | NYA |  | NYA
| NHS or not | 0 | NYA |  | NYA
| Data Controller(s) |  | NYA |  | NYA
| Data Processor(s) |  | NYA |  | NYA
| Date Submitted | 0 | NYA |  | NYA
Data Protection Act Information
| DPA Registration |  | NYA |  | NYA
| FPN |  | NYA |  | NYA
Existing Data Sharing Framework Contract
| Reference | 0 | NYA |  | NYA
| NHS Digital Signature | 0 | NYA |  | NYA
| Expiry Date | 0 | NYA |  | NYA
Existing Data Sharing Agreement
| Reference | 0 | NYA |  | NYA
| NHS Digital Signature | 0 | NYA |  | NYA
| Expiry Date | 0 | NYA |  | NYA
Local Data Sharing Agreements
| Local DSA |  | NYA |  | NYA
PDS Data and Access Method
| PDS data already held |  | NYA |  | NYA
| Current Method | 0 | NYA |  | NYA
| PDS data requested |  | NYA |  | NYA
| Requested Method | 0 | NYA |  | NYA
| Application provider |  | NYA |  | NYA
| RA | 0 | NYA |  | NYA
Request Details
| Objectives and Purpose |  | NYA |  | NYA
| Context Diagram |  | NYA |  | NYA
| Business Processes |  | NYA |  | NYA
| System Processes |  | NYA |  | NYA
| Outputs |  | NYA |  | NYA
| Benefits |  | NYA |  | NYA
User information
| User roles |  | NYA |  | NYA
| Numbers of |  | NYA |  | NYA
| Target date | 0 | NYA |  | NYA
Legal Basis
| Statutory Functions |  | NYA |  | NYA
| Legal Basis for data release |  | NYA |  | NYA
| H&SC Act 2012 ref. |  | NYA |  | NYA
| Legal Basis for data receipt |  | NYA |  | NYA
| Relevant Sections |  | NYA |  | NYA
Security and IG Assurance
| IGT Version |  | NYA |  | #REF!
| IGT Score | #REF! | NYA |  | NYA
| Date | #REF! | NYA |  | NYA
| Review Result | #REF! | NYA |  | NYA
| Date | #REF! | NYA |  | NYA
| ISO 27001 |  | NYA |  | NYA
| Security Policy |  | NYA |  | NYA
| Main Data Centre |  | NYA |  | NYA
| Jurisdiction | England / Wales | NYA |  | NYA
|  |  | NYA |  | NYA
| Backup Data Centre |  | NYA |  | NYA
| Jurisdiction | England / Wales | NYA |  | NYA
|  |  | NYA |  | NYA
| Territory | England / Wales | NYA |  | NYA
|  |  | NYA |  | NYA
Client IGSoC Status - N3/HSCN connections
| Organisation Type | 0 | NYA |  | #REF!
| Date Started | 0 | NYA |  | #REF!
| Date Published | 0 | NYA |  | #REF!
| Self-assessed Grade | 0 | NYA |  | #REF!
Third Party Supplier Details
| Product(s) |  | NYA |  | NYA
| Supplier(s) |  | NYA |  | NYA
| Technically assessed? |  | NYA |  | NYA
| Purpose |  | NYA |  | NYA
| First of Type |  | NYA |  | NYA
| Version & configuration |  | NYA |  | NYA
| Service aggregation |  | NYA |  | NYA

## Lists
NHS Digital Use Only - DO NOT EDIT
PDS IG Scrutiny Drop-down Lists and Definitions
RAG | Risk Status
Red | High Risk
Amber | Medium Risk
Green | Limited or No Risk
Comp-lete | No further action
N/A | Not applicable
None Yet | Not yet assessed
Org Type
Acute Trust
Ambulance Trust
Any Qualified Provider - Clinical Services
Any Qualified Provider - Non Clinical Services
Clinical Commissioning Group
Commercial Third Party
Commissioning Support Unit
Community Health Provider
Community Pharmacy/DAC
Data Service for Commissioners
Dental Practice
Eye Care Service
General Practice
Hosted Secondary Use Team/Project
Local Authority
Mental Health Trust
NHS Business Partner/ITC/ALB
NHS Business Services Authority
NHS Digital
NHS England
Prison Health
Public Health England
Secondary Use Organisation
Voluntary Sector Organisation
End User Org
NYA | Not yet allocated
N/A | Not applicable
CCG | Clinical Commissioning Group
CIC | Community Interest Corporation (usually former PCT community services)
CSU | Commissioning Support Unit (and the like)
Govt | Government Department
GP | GP Practices
ISHP | Independent Sector Healthcare Provider
LA | Local Authority
Trust | NHS Healthcare provider
NHS or Not
NYK | Not yet known
NHS | eg, trust, GP practice, etc
Non-NHS | eg, ISHP, servive provider
Mixed | Mixed NHS and Non-NHS staff
Purpose
NYA | Not yet allocated
Direct Care | Delivery of health care or social care
Other | No single category applies - explained in "Objects/Purpose".
PHIN | Data to Private Health Information Network
PROMS | PROMS Questionnaires
PDS Access Method
NYK | Not yet known
Spine Full | Full Spine Integrated system
Soine Partial | Partial Spine Integrated system
SMSP | Spine Mini Services Provider
SCRa | Summary Care Record Application
DBS | Demographics Batch Service
DBS BS | Demographics Batch Service Bureau Service
N/A | Not Applicable
IGT Review Result
NYK | Not yet known
Not Complete
Not Satisfactory
Improvement
Satisfactory
IGsOC Result
Not Complete
Not Satisfactory
Improvement
Satisfactory
Jurisdiction
England / Wales
UK | Incudes Scotland and NI / not Isle of Man or Channel Islands
EEA | European Economic Area / includes Isle and Man and Channel Islands
Other | eg, outside EEA
Assessment Scores
NYA | Not yet assessed
OK | Information sufficiently complete and satisfactory
Not OK | Information incomplete or ambiguous or not satisfactory
Queries | Queries outstanding
PDS IG Scrutiny Category
NYK | Not yet known
Risk Assess | Undergoing risk assessment
A - IAO | Sign-off by PDS IAO
A - SIRO | Sign-off by SIRO
B - IGARD 1st | Submit to IGARD as 1st of Type
B - IGARD 2nd | Submit to IGARD as Subsequent of Type
Approval
Approved
Rejected
UsageOutcome
The usage and settings statement has been fully approved - no further usage and settings assessment required
The usage and settings statement has been approved - a DSFC and DSA must be sought
The usage and settings statement has been approved - DSA must be sought
The usage and settings statement has been provisionally approved - full approval will be sought through the IGARD process
The usage and settings statement has been rejected